## Hiferr Mobile app (Android)
Hiferr Mobile App (Andorid)
|  | GANTT Chart : Hiferr Mobile app (Android) Release ID: Augurs Tech: Protected Controlled Copy Project ID:ATPL07292022 <SCI.ID.> / Ver: 01.0 |  |  | Resources |  | Dev 1
Backend dev
[7 empty] | Project Start Date | 2022-08-03 |  | August | [56 empty] | September | [30 empty] | October | [21 empty] | September | [22 empty] | October
 | time axis 2022-08-03 to 2023-01-27
S# | Requirement ID | Task Description | Milestone | Resource | Resrouce | Weekday Duration | Weekday Duration | Start | End | time axis 2022-08-03 to 2023-01-27
1 | BR001 | > UI/UX development In PNG (Both android and Ios) - Splash screen - Phone number enter screen - OTP screen for verification of the number - Sign up page - - Meet screen - Create meet & Profile page - Add profile & pics with multiple profile - Open dropdown page - Add and create keywords - Add religion dropdown - Status dropdown - Ethnic background - Qualification - Current location with profile data - List of meet people - List fetch with profile location - Search profiles - Skills - Show profile detail with search results highlights match keyword - Give option to msg user - Create filter - Add filter data source - Matched profile with filter data source - Show profile according to filter - Profile page (Account setting, Profile icon image edit and change, email , phone number, toggle on/off for message and notifications, delete your account, invite friends , app version info at the bottom, unblock the blocked user) - Flash screen page with features - Chat page ( list of chat user’s , search chat , chat notification , clicking on any chat will open chat box, last seen - - Profile page (Account setting, Profile icon image edit and change, email , phone number, toggle on/off for message and notifications, delete your account, invite friends , app version info at the bottom, unblock the blocked user) - Chat page ( list of chat user’s , search chat , chat notification , clicking on any chat will open chat box, last seen) - Internal testing and fixes | MS-1 | Dev 1 |  |  | 5 | 2022-08-03 | 2022-08-09 | bar: 2022-08-06 to 2022-08-07
2 | BR002 | > Development & Functionality (Android ) - XML design of the splash screen, sign up , Phone number to login , OTP verification screen - Sign up and its implementation - Phone number SMS Key API integration - Internal testing and fixes | MS-2 | Dev 1 | Backend dev | 5 | 5 | 2022-08-10 | 2022-08-19
3 | BR003 | > Development & Functionality (Android ) - Meet screen XML design and features development - Create meet & Profile page - Add profile & pics with multiple profile - Open dropdown page - Add and create keywords - Add religion dropdown - Status dropdown - Ethnic background - Qualification - Current location with profile data - List of meet people - List fetch with profile location - Internal testing and fixes | MS-3 | Dev 1 |  |  | 10 | 2022-08-20 | 2022-09-02
4 | BR004 | > Development and Functionality (Android) - Search profile in meet section development on the basis of keywords - Skills - Show profile detail with search results highlights match keyword - Give option to msg user - Internal testing and fixes | MS-4 | Dev 1 |  |  | 10 | 2022-09-05 | 2022-09-18
5 | BR005 | > Development & Functionality (Android) - Create filter - Add filter data source - Matched profile with filter data source - Show profile according to filter - Internal testing and fixes | MS-5 | Dev 1 |  |  | 10 | 2022-09-19 | 2022-09-30
6 | BR006 | > Development & Functionality (Android) - Profile page development (All the features such as profile edit, notification toggle, app version, unblock the block users , T& C Privacy policy etc) - Flash screen development in XML as per the features - Latest status comes on top with date and time for every status - Flash features complete development - Internal testing and fixes | MS-6 | Dev 1 |  |  | 10 | 2022-10-01 | 2022-10-07
7 | BR007 | > Development & Functionality (Android) - Chat screen development in XML as per the features - Real time chat integration through firebase - Last seen , online user - Read /unread messages etc. - Internal testing and fixes - Notification functionality though firebase - All the live notifications splashes - Other features - Internal testing and fixes - UAT - Finalization of the app | MS-7 | Dev 1 |  |  | 10 | 2022-10-10 | 2022-10-23
0
Holiday
[7 empty] | 2021-01-01 | 2021-01-01
[7 empty] | 2021-01-14 | 2021-01-14