## Hiferr Mobile app (ios)
Hiferr Mobile App (ios)
|  | GANTT Chart : Hiferr Mobile app (ios) Release ID: Augurs Tech: Protected Controlled Copy Project ID:ATPL07292022 <SCI.ID.> / Ver: 01.0 |  |  | Resources |  | Dev 1
[7 empty] | Project Start Date | 2022-08-03 |  | August | [56 empty] | September | [30 empty] | October | [21 empty] | September | [22 empty] | October
 | time axis 2022-08-03 to 2023-01-27
S# | Requirement ID | Task Description | Milestone | Resource | Resrouce | Weekday Duration | Weekday Duration | Start | End | time axis 2022-08-03 to 2023-01-27
1 | BR001 | > Development & Functionality( ios) - XML design of the splash screen, sign up , login with Phone number screen , OTP verification screen - Phone number SMS Key API integration - Sign up API creation and its implementation - Internal testing and fixes | MS-1 | Dev 1 |  |  | 5 | 2022-08-03 | 2022-08-09 | bar: 2022-08-06 to 2022-08-07
2 | BR002 | > Development & Functionality( ios) - Meet screen XML design and features development - Create meet & Profile page - Add profile & pics with multiple profile - Open dropdown page - Add and create keywords - Add religion dropdown - Status dropdown - Ethnic background - Qualification - Current location with profile data - List of meet people - List fetch with profile location - Internal testing and fixes | MS-2 | Dev 1 |  |  | 10 | 2022-08-10 | 2022-08-25
3 | BR003 | > Development and Functionality ( ios) - Search profile in meet section development on the basis of keywords - Skills - Show profile detail with search results highlights match keyword - Give option to msg user - Internal testing and fixes | MS-3 | Dev 1 |  |  | 8 | 2022-08-26 | 2022-09-08
4 | BR004 | > Development & Functionality (ios) - Create filter - Add filter data source - Matched profile with filter data source - Show profile according to filter - Internal testing and fixes | MS-4 |  |  |  | 12 | 2022-09-09 | 2022-09-26
5 | BR005 | > Development & Functionality (ios) - Profile page development (All the features such as profile edit, notification toggle, app version, unblock the block users , T& C Privacy policy etc) - Internal testing and fixes | MS-5 |  |  |  | 5 | 2022-09-27 | 2022-10-05
6 | BR006 | > Development & Functionality (ios) - Flash screen development in XML as per the features - Latest status comes on top with date and time for every status - Flash features complete development - Internal testing and fixes | MS-6 |  |  |  | 10 | 2022-10-06 | 2022-10-19
7 | BR007 | > Development & Functionality (ios) - Chat screen development in XML as per the features - Real time chat integration through firebase - Last seen , online user - Read /unread messages etc. - Internal testing and fixes - Notification functionality though firebase - All the live notifications splashes - Other features - Internal testing and fixes - UAT - Finalization of the app | MS-7 | Dev 1 |  |  | 10 | 2022-10-20 | 2022-11-02
0
Holiday
[7 empty] | 2021-01-01 | 2021-01-01
[7 empty] | 2021-01-14 | 2021-01-14